## Grant Info2
| Year | Project No | Applicant | Applicant Charity No | Project Name | Amount Requested | Decision | CF or OSR or Play (reason for spend) | Pd? | Member Grant Panel Date | Exec Decision Date | Parish Area | Development/s Funding Project | Spend by date for allocated money | Date to be completed by as per T and Cs | Total time given to deliver project | Project Completed? ….. | Projected-Date-For-Completion…. | Monitoring Report Received (date) | Additional Monitoring Notes
| 2008 | n/a | Lutterworth Town Council |  | Provision of play area in Coventry Road | n/a | £15,000 paid in April 2008 & £10,000 paid in August 2008 |  |  |  |  | Lutterworth | Inforamtion not available
| 2008 | n/a | Husbands Bosworth Allotment Group |  | Purchase picnic table and papasol | n/a | REFUSED |  |  |  |  | Husbands Bosworth | Inforamtion not available
| 2008 | n/a | Turville Memorial Hall |  | Replacement windows | n/a | REFUSED |  |  |  |  | Husbands Bosworth | Inforamtion not available
| 2008 | n/a | Husbands Bosworth Methodist Church |  | Replace heating system | n/a | REFUSED |  |  |  |  | Husbands Bosworth | Inforamtion not available
| 2008 | n/a | All Saints Church Husbands Bosworth |  | Renewing kitchen, disabled toilets, ramp, resurfacing car park & drive. | n/a | REFUSED |  |  |  |  | Husbands Bosworth | Inforamtion not available
| 2008 | n/a | St Lukes Church, Thurnby |  | Access ramp | n/a | REFUSED |  |  |  |  | Thurnby & Bushby | Inforamtion not available
| 2008 | n/a | Team MBM Cycling Club |  | Website & equipment | n/a | REFUSED |  |  |  |  | Broughton Astley | Inforamtion not available
| 2008 | n/a | TABASC |  | new table tennis tables | n/a | REFUSED |  |  |  |  | Thurnby & Bushby | Inforamtion not available
| 2008 | n/a | HDC |  | Lubenham Hill activated road sign | n/a | REFUSED |  |  |  |  | Harborough | Inforamtion not available
| 2008 | n/a | Belgrave Village Hall |  | New bar, connection of drainage to sewer | n/a | £9750.00 paid in April 2008 |  |  |  |  | North Kilworth | Inforamtion not available
| 2008 | n/a | Great Glen Parish Council |  | Skate Park | n/a | £25,000 paid in July 2008 |  |  |  |  | Great Glen | Inforamtion not available
| 2008 | n/a | Kibworth & District U3A |  | Expand activities to accommodate increased membership | n/a | £16,621 paid in July 2008 |  |  |  |  | Kibworth | Inforamtion not available
| 2008 | n/a | Husbands Bosworth CofE Primary School |  | Relaying the school playground | n/a | £23952.32 put on hold awaiting funding. |  |  |  |  | Husbands Bosworth | Inforamtion not available
| 2008 | n/a | Broughton Astley Parish Council |  | Replacement changing facilities at Frolesworth Rd recreation ground | n/a | £51,357 paid in July 2008 |  |  |  |  | Broughton Astley | Inforamtion not available
| 2008 | n/a | Broughton Astley Parish Council |  | Frolesworth Road hedge | n/a | £800 paid in July 2008 |  |  |  |  | Broughton Astley | Inforamtion not available
| 2008 | n/a | Husbands Bosworth Parish Council |  | New play equipment at Kilworth Road | n/a | £10,800 paid in July 2008 |  |  |  |  | Husbands Bosworth | Inforamtion not available
| 2008 | n/a | Husbands Bosworth Tennis Club |  | Floodlights & resurfacing 2 courts | n/a | £26,000 paid in July 2008 |  |  |  |  | Husbands Bosworth | Inforamtion not available
| 2008 | n/a | Husbands Bosworth Parish Council |  | Millenium Woodland - create a boardwalk across the pond | n/a | £10,000 paid in July 2008 |  |  |  |  | Husbands Bosworth | Inforamtion not available
| 2008 | n/a | Fleckney Parish Council |  | All weather floodlit multi use games area | n/a | £20,000 paid in July 2008 |  |  |  |  | Fleckney | Inforamtion not available
| 2008 | n/a | Husbands Bosworth Millenium Sports Fund |  | Install fence between play area & car park | n/a | £5,295 paid in July 2008 |  |  |  |  | Husbands Bosworth | Inforamtion not available
| 2008 | n/a | Lutterworth Town Hall Charity |  | Renew kitchen at Town Hall | n/a | £12,800 paid in July 2008 |  |  |  |  | Lutterworth | Inforamtion not available
| 2008 | n/a | HDC |  | Play equipment at Logan Street Recreation Ground | n/a | £32,000 paid in July 2008 |  |  |  |  | Market Harborough | Inforamtion not available
| 2008 | n/a | HDC |  | Skate Park at Bellfields | n/a | £100,000 paid in July 2008 |  |  |  |  | Market Harborough | Inforamtion not available
| 2008 | n/a | Market Harborough Drama Society |  | Life installations at Market Harborough theatre | n/a | £40,000 paid in July 2008 |  |  |  |  | Market Harborough | Inforamtion not available
| 2008 | n/a | Harborough Improvement team |  | Provision of noticeboards in Market Harborough | n/a | £3,300 paid in July 2008 |  |  |  |  | Market Harborough | Inforamtion not available
| 2008 | n/a | Sir Frank Whittle Commemorative Trust |  | Floodlighting & maintenance of aircraft at roundabout | n/a | £3000 paid in July 2008 |  |  |  |  | Lutterworth | Inforamtion not available
| 2008 | n/a | Kibworth Joint Recreation Committee |  | grant towards phase 2 of the Warwick Road Childrens playground improvement scheme | n/a | £45,000 paid in April 2008 |  |  |  |  | kibworth | Inforamtion not available
| 2008 | n/a | Harborough Town Football Club |  | towards extension/alterations to existing clubhouse | n/a | £90,000 paid in April 2008 |  |  |  |  | Market Harborough | Inforamtion not available
| 2008 | n/a | Fleckney Skate Park Committee |  | Fleckney Skatepark project | n/a | £20,000 paid in April 2008 |  |  |  |  | Fleckney | Inforamtion not available
| 2008 | n/a | Harborough Town Juniors FC |  | Surfacing of new car park & landscaping | n/a | REFUSED |  |  |  |  | Market Harborough | Inforamtion not available
| 2008 | n/a | TABSASA |  | New grounds maintenance store & replacement windows | n/a | £13463.31 paid in Jan 2009 |  |  |  |  | Thurnby & Bushby | Inforamtion not available
| 2008 | n/a | Thurnby & Bushby Playgroup |  | All weather canopy at St Luke's School | n/a | £4,908 paid in Jan 2009 |  |  |  |  | Thurnby & Bushby | Inforamtion not available
| 2008 | n/a | Thurnby Memorial Hall |  | New heating boiler & windows | n/a | £4,908 paid in Jan 2009 |  |  |  |  | Thurnby & Bushby | Inforamtion not available
| 2008 | n/a | Thurnby Scout & Guide Group |  | Extension & disabled facilities | n/a | £4,908 paid in Jan 2009 |  |  |  |  | Thurnby & Bushby | Inforamtion not available
| 2008 | n/a | Great Glen Parish Council |  | Play equipment & safe surfacing | n/a | £4,180 paid in Jan 2009 |  |  |  |  | Great Glen | Inforamtion not available
| 2008 | n/a | HFM Radio Ltd |  | Studio Equipment | n/a | £5,500 paid in Jan 2009 |  |  |  |  | Market Harborough | Inforamtion not available
| 2008 | n/a | HDC |  | Manor Field Play Equipment & Installation of Wadkins Field path | n/a | £100,000 paid in Jan 2009 |  |  |  |  | Thurnby & Bushby | Inforamtion not available
| 2008 | n/a | HDC |  | Footpath/cycleway at Little Bowden Recreation Ground | n/a | £41,000 paid in Jan 2009 |  |  |  |  | Little Bowden | Inforamtion not available
| 2008 | n/a | St Dionysius Church |  | Refurbishment of Town Clock | n/a | £1,500 paid in Jan 2009 |  |  |  |  | Market Harborough | Inforamtion not available
| 2008 | n/a | St Lukes CofE School |  | Play equipment | n/a | £4,908 paid in Jan 2009 |  |  |  |  | Thurnby & Bushby | Inforamtion not available
| 2008 | n/a | TABSASA |  | 3rd Tennis Court | n/a | £13,463.31 paid in Jan 2009 |  |  |  |  | Thurnby & Bushby | Inforamtion not available
| 2009 | n/a | Lutterworth Radio |  | Recording Equipment | n/a | £315 paid in June 2009 |  |  |  |  | Lutterworth | Inforamtion not available
| 2009 | n/a | Lutterworth Town Council |  | Landscaping of Memorial Garden | n/a | £25,000 paid in June 2009 |  |  |  |  | Lutterworth | Inforamtion not available
| 2009 | n/a | St Mary's Church |  | Imporvements to the churchyard boundary & installation of lighting | n/a | £10,000 paid in June 2009 |  |  |  |  | Lutterworth | Inforamtion not available
| 2009 | n/a | The Well Project |  | The Well refurbishment | n/a | REFUSED |  |  |  |  | Kibworth Beauchamp | Inforamtion not available
| 2009 | n/a | HDC |  | Symingtons Recreation Ground improvement | n/a | Paid £91,000 |  |  |  |  | Harborough | Inforamtion not available
| 2009 | n/a | Lutterworth Athletic FC |  | Provision of Floodlights | n/a | Paid £10,000 in November 2009 |  |  |  |  | Lutterworth | Inforamtion not available
| 2009 | n/a | Ullesthorpe Playing Field Association |  | Pathway with lighting | n/a | £2,208.88 paid in November 2009 |  |  |  |  | Ullesthorpe | Inforamtion not available
| 2009 | n/a | All Saints Church Swinford |  | Church clock motor | n/a | £1,340 paid in November 2009 |  |  |  |  | Swinford | Inforamtion not available
| 2009 | n/a | Scraptoft Village Hall |  | Loop system for hard of hearing | n/a | £1875.90 paid in November 2009 |  |  |  |  | Scraptoft | Inforamtion not available
| 2009 | n/a | Scraptoft Parish Council |  | Installation of vehicle activeated sign in Scraptoft | n/a | £8,000 paid in November 2009 |  |  |  |  | Scraptoft | Inforamtion not available | [6 empty] | mailto:m.jennings@harborough.gov.uk?subject=Spreadsheet
| 2009 | n/a | St Johns Ambulance Lutterworth CFR |  | Additional equipment and vehicle GPS system | n/a | £9,000 paid in November 2009 |  |  |  |  | Lutterworth | Inforamtion not available
| 2009 | n/a | Harborough Wheels Project |  | Refurbishment of Skate Bowl facility in Bellfields Rectreation Ground, Little Bowden | n/a | £50,000 agreed in July 2011 |  |  |  |  | Little Bowden | Inforamtion not available
| 2009 | n/a | Harborough in Bloom Volunteers |  | Garden Project at Welland Park | n/a | £7,500 paid May 2010 |  |  |  |  | Harborough | Inforamtion not available
| 2009 | n/a | HDC |  | Welland Park Car Park | n/a | [5 empty] | Harborough | Inforamtion not available
| 2009 | n/a | Ullesthorpe Parish Council |  | Landscaping | n/a | [5 empty] | Ullesthorpe | Inforamtion not available
| 2009 | n/a | Stoughton Village Hall Management Committee |  | Double Glazing & Heating of Village Hall | n/a | £1,800.31 paid September 2009 |  |  |  |  | Stoughton | Inforamtion not available
| 2009 | n/a | Swinford Parish Council |  | Extension of village cemetry | n/a | £7,300 paid in July 2009 |  |  |  |  | Swinford | Inforamtion not available
| 2009 | n/a | Old Mill Primary School |  | Installation of play train | n/a | £2,500 paid in November 2009 |  |  |  |  | Broughton Astley | Inforamtion not available
| 2009 | n/a | Lutterworth Rugby FC |  | Improvement to pitch drainage | n/a | £5,000 paid in November 2009 |  |  |  |  | Lutterworth | Inforamtion not available
| 2009 | n/a | Kibworth Art Lovers Society |  | Exhibition Screen | n/a | REFUSED |  |  |  |  | Kibworth | Inforamtion not available
| 2009 | n/a | Broughton Astley Parish Council |  | Extension of cremated remains butial area, contruction of turning head parking space for elderly & disabled visitors | n/a | £15,640 paid in June 2009 |  |  |  |  | Broughton Astley | Inforamtion not available
| 2009 | n/a | Lutterworth Cricket Club |  | Extension to existing pavillions | n/a | £10,000 paid in June 2009 |  |  |  |  | Lutterworth | Inforamtion not available
| 2009 | n/a | Little Bowden Bowling Club |  | Replacement of ditches | n/a | £3,000 paid in June 2009 |  |  |  |  | Harborough | Inforamtion not available
| 2009 | n/a | Lutterworth High School |  | Sensory and Wildlife Garden Project | n/a | £7,500 paid in 2009 |  |  |  |  | Lutterworth | Inforamtion not available
| 2009 | n/a | Our Lady of Victories Community Hall |  | Renewal of 2 community rooms & 2 kitchens | n/a | £4,625 paid |  |  |  |  | Harborough | Inforamtion not available
| 2009 | n/a | Our Lady of Victories Community Hall |  | Refurbishment (It appears £5,000 was awarded in 2008 & £5,000 was awarded in 2009) | n/a | £5,000 paid Jan 2009 - this would be out of the 2008 budget. £1,588 paid in June 2009. £1,507.13 paid in August 2009. 31,904.87 paind in October 2009 |  |  |  |  | Harborough | Inforamtion not available
| 2009 | n/a | Swinford Village Hall |  | Kitchen Appliances / Tables | n/a | 2257.7 |  |  |  |  | Swinford | Inforamtion not available
| 2009 | n/a | Aylestone St James RFC |  | Refurbishment | n/a | REFUSED |  |  |  |  | Scraptoft | Inforamtion not available
| 2010 | n/a | Great Easton Recreation Ground Committee |  | new play equipment | n/a | £11,475 paid in Oct 2010 | [5 empty] | Inforamtion not available
| 2010 | n/a | Kibworth Beauchamp Parish Council |  | Two new bus shelters | n/a | £19,858 paid in Feb 2011 |  |  |  |  | Kibworth | Inforamtion not available
| 2010 | n/a | Broughton Astley Parish Council |  | Creation of additional allotments | n/a | 11635 |  |  |  |  | Broughton Astley | Inforamtion not available
| 2010 | n/a | Ashby Parva Parish Meeting |  | Various | n/a | £3,143.64 paid in Aug 2010 |  |  |  |  | Ashby Parva | Inforamtion not available
| 2010 | n/a | St Mary's Parish Church Parochial Church Council |  | 3 benches for churchyard | n/a | £2,085 paid in Jan 2011 |  |  |  |  | Lutterworth | Inforamtion not available
| 2010 | n/a | Fleckney Parish Council |  | supply & install of play equipment and alterations to existing play area | n/a | £10,000 paid in Jan 2011 |  |  |  |  | Fleckney | Inforamtion not available
| 2010 | n/a | 1st Market Harborough Scout Group |  | building extension | n/a | Only application form on file |  |  |  |  | Market Harborough | Inforamtion not available
| 2010 | n/a | 1st Broughton Astley Scout Group |  | building refurbishment | n/a | Only application form on file |  |  |  |  | Broughton Astley | Inforamtion not available
| 2010 | n/a | Misterton with Walcote Parish Council |  | New play area | n/a | Only application form on file |  |  |  |  | Mistertoh | Inforamtion not available
| 2010 | n/a | Swinford 2000 |  | Minibus | n/a | Only application form on file |  |  |  |  | Lutterworth | Inforamtion not available
| 2010 | n/a | Kibworth Beauchamp Parish Council |  | Refurbish Village Hall | n/a | Only application form on file |  |  |  |  | Kibworth | Inforamtion not available
| 2010 | n/a | Swinford Village Hall |  | Kitchen Refurb | n/a | Only application form on file |  |  |  |  | Lutterworth | Inforamtion not available
| 2010 | n/a | HDC |  | Multi games area, Little Bowden | n/a | Only application form on file |  |  |  |  | Little Bowden | Inforamtion not available
| 2010 | n/a | HDC |  | Upgrade public spaces & CCTV camera | n/a | Only application form on file |  |  |  |  | Market Harborough | Inforamtion not available
| 2010 | n/a | The Robert Smyth School |  | New cantee facilities | n/a | Only application form on file |  |  |  |  | Market Harborough | Inforamtion not available
| 2010 | n/a | Swinford Village Hall |  | enclosed outdoor play area | n/a | Only application form on file |  |  |  |  | Lutterworth | Inforamtion not available
| 2011 | n/a | Thurnby United Reform Church |  | Improved access & disabled toilet facilities | n/a | Deferred |  |  |  |  | Thurnby & Bushby | Inforamtion not available
| 2011 | n/a | Stoughton Parish Council |  | Installations of pathways & open space improvements | n/a | £40,042.62 paid in Nov 2011 | [5 empty] | Inforamtion not available
| 2011 | n/a | Scrapcroft Parish Council |  | Seats & litter bins at Woodland Walk | n/a | £4,000 paid in Nov 2011 | [5 empty] | Inforamtion not available
| 2011 | n/a | HDC |  | Construction of footway link at Simborough Way Open Space | n/a | £13,500 paid in Nov 2011 | [5 empty] | Inforamtion not available
| 2011 | n/a | Skeffington Parish Meeting |  | Benches & Street Scene Improvements | n/a | £1,700 paid in Nov 2011 | [5 empty] | Inforamtion not available
| 2011 | n/a | HDC |  | Construction of play area at Coales Gardens | n/a | £35,000 paid in Nov 2011 | [5 empty] | Inforamtion not available
| 2011 | n/a | Swinford 2000 |  | Additional play equipment | n/a | £14,377 paid in Nov 2011 | [5 empty] | Inforamtion not available
| 2011 | n/a | Swinford 2000 |  | Purchase of minibus | n/a | REFUSED | [5 empty] | Inforamtion not available
| 2011 | n/a | Friends of Welland Park |  | Improved tennis facilities including floodlighting | n/a | £56,000 paid in Nov 2011 | [5 empty] | Inforamtion not available
| 2011 | n/a | All Saints Parochial Church Council |  | Church heating | n/a | REFUSED | [5 empty] | Inforamtion not available
| 2011 | n/a | St Wilfred's Church |  | External works | n/a | Deferred |  |  |  |  | Kibworth | Inforamtion not available
| 2011 | n/a | Lutterworth Town Council |  | new play equipment at Crescent Road & Coventry Road | n/a | £3,909 paid in Nov 2011 |  |  |  |  | Lutterworth | Inforamtion not available
| 2011 | n/a | Lutterworth Town Council |  | levelling of Moorbarns Lane and the provision of goal posts | n/a | £8,074 paid in Nov 2011 |  |  |  |  | Lutterworth | Inforamtion not available
| 2011 | n/a | Harborough Wheels Project |  | Floodlighting at Bellfields Skatepark | n/a | £25,000 paid in Nov 2011 |  |  |  |  | Market Harborough | Inforamtion not available
| 2011 | n/a | HYACT |  | renovation of Bowls Pavilion to make a youth Club | n/a | £63,103 paid in Nov 2011 |  |  |  |  | Market Harborough | Inforamtion not available
| 2011 | n/a | Skeffington Parish Meeting |  | Purchase of land for use of play area | n/a | 53422 | [5 empty] | Inforamtion not available
| 2011 | n/a | Skeffington Parish Meeting |  | Cemetery improvements | n/a | £6,600 paid in Nov 2011 |  | Y |  |  |  | Inforamtion not available
| 2012 | n/a | Kibworth History Society |  | Purchase of computer equipment | n/a | REFUSED |  |  |  |  | Kibworth | Inforamtion not available |  | n/a
| 2012 | n/a | Market Harborough In Bloom Volunteers |  | Mini golf facility in Welland Park | n/a | 28474.35 |  | not paid. Grant retracted as didn’t secure funding by completion date |  | 2012-10-01 | MH | Inforamtion not available |  | 01/08/2013 BUT extended to August 2014
| 2012 | n/a | The Kibworth Band |  | New UPVC style windows. | n/a | 2815 |  | Y |  | 2012-10-01 | Kibworth | Inforamtion not available |  | 2013-02-01
| 2012 | n/a | 1st Market Harborough Scout Group |  | Extension and refurbishment of scout building | n/a | £22,199.80 (awaiting payment with secured match funding) |  | Y |  | 2012-10-01 | MH | Inforamtion not available |  | 2013-10-01
| 2012 | n/a | Swinford Village Hall |  | Replacement of 5 windows and 4 outside fire doors in the Village Hall. | n/a | REFUSED |  |  |  | 2012-10-01 | Swinford | Inforamtion not available |  | n/a
| 2012 | n/a | Harborough Improvement Team |  | Welland Park Café | n/a | £22,199.80 (awaiting payment with secured match funding) |  | not paid. Grant retracted as didn’t secure funding by completion date |  | 2012-10-01 | MH | Inforamtion not available |  | 2014-03-01
| 2012 | n/a | All Saints Scraptoft Youth Group |  | Portable Skate Facility | n/a | 5000 |  |  |  | 2012-10-01 | Scraptoft | Inforamtion not available |  | 2013-08-01
| 2012 | n/a | Market Harborough RUFC |  | 1923 Project. Extension to current changing block and internal modifications to existing clubhouse space including catering space. | n/a | 68000 |  | Y |  | 2012-10-01 | MH | Inforamtion not available |  | 2013-09-01 |  |  |  | emailed 10/15 & 3/16 requesting completion report -
| 2012 | n/a | Great Glen Tennis Club |  | Three new tennis courts | n/a | REFUSED |  | n/a |  | 2012-10-01 | Great Glen | Inforamtion not available |  | n/a
| 2012 | n/a | St Wilfrid's Church |  | Improve access to the church | n/a | 24760.75 |  | Y |  | 2012-10-01 | Kibworth | Inforamtion not available |  | 2013-09-01 |  |  |  | progress email sent - job complete but no completion report. Sent reminder 10/15 & 2/16
| 2012 | n/a | Fleckney Parish Council |  | Multi-use pitch | n/a | 10000 |  | Y |  | 2012-10-01 | Fleckney | Inforamtion not available |  | 2013-03-01 |  | Yes
| 2013/2014 | ROUND ONE
| 2013/2014 | 001 R1 S016 13/14 | Aylestone St James RFC |  | Extension to clubhouse | 24500 | 25000 | CF | Grant Declined | 9th October 2013 | 12th November 2013 | Scraptoft | Former Demontford Campus |  | 2016-10-01 |  | n/a |  | Update received oct 2014. hayley following up 23/06/2015 | GRANT RETURNED - SEE GRANT FILE T&C'S FOR DETAILSno elec filed T&C HC contacted 19/8
| 2013/2014 | 002 R1 S016 13/14 | Great Bowden Parish Council |  | Extension to Pavilion Changing Rooms | 24500 | 24000 | CF | Y | 9th October 2013 | 12th November 2013 | Great Bowden | Former Fernie Stable |  | 2015-10-01 | 23 Months | completed Oct 15 |  | Completed
| 2013/2014 | 003 R1 S016 13/14 | Great Bowden Parish Council |  | Installation of Solar Panels to existing community pavillion | 17491 | REFUSED |  | N/A | 9th October 2013 | 12th November 2013 | Great Bowden |  |  | N/A | N/A | n/a | N/A | N/A
| 2013/2014 | 004 R1 S106 13/14 | Great Bowden Parish Council |  | To refurbish currently closed toilets | 8000 | REFUSED |  | N/A | 9th October 2013 | 12th November 2013 | Great Bowden |  |  | n/a | N/A | n/a | N/A | N/A
| 2013/2014 | 006 R1 S106 13/14 | Kibworth Joint Burial Committee |  | Tarmac pathway to parish cemetery | 5000 | 6000 | OSR | Y | 9th October 2013 | 12th November 2013 | Kibworth | Kibworth Cricket Club |  | 2014-10-01 | 11 months | completed- 01/05/2014 | n/a | 2014-10-01
0 | 2013/2014 | 007 R1 S106 13/14 | Kibworth Joint Recreation Committee |  | Conversion of land to convert to parish allotments | 41500 | 41000 | OSR | Y | 9th October 2013 | 12th November 2013 | Kibworth | Kibworth Cricket Club |  | 2014-06-01 | 8 months | completed 31/12/13 | N/A | 2014-10-01
| 2013/2014 | 008 R1 S106 13/14 | Market Harborough Squash and Racketball Club |  | Extension to include 2 new glass backed courts | 100000 | 16884 | OSR | Y | 9th October 2013 | 12th November 2013 | Market Harborough | Former Rubber Fatory Site |  | 2015-10-01 | 23 months | Completed Nov 15 | Summer 2015 | completed and filed 28/03/2017 ENE
| 2013/2014 | 009 R1 S106 13/14 | Market Harborough Football Club | 1126014 | Construct Flood Barrier | 20636 | 20636 | OSR | Y | 9th October 2013 | 12th November 2013 | Market Harborough | Former Rubber Fatory Site |  | 2014-04-01 | 6 months | -completed Nov 2014 | n/a | Completed report on file
| 2013/2014 | 010 R1 S106 13/14 | North Kilworth Parish Council |  | Play Equipment | 4313 | 4313.68 | Play | Y | 9th October 2013 | 12th November 2013 | North Kilworth | Station Garage, Station Road |  | 2015-10-01 | 11 months | completed July 2014 | N/a | Completed report on file 01/10/2014
| 2013/2014 | 011 R1 S106 13/14 | Thurnby and Bushby Sports association |  | Feasibilty Study to determine current structure of the building to establish fit for purpose (use existing funds) |  | REFUSED |  | N/A | 9th October 2013 | 12th November 2013 | Thurnby Parish Council |  |  | N/A | N/A | n/a | N/A | N/A
| 2013/2014 | 012 R1 S106 13/14 | Broughton Astley Community Bus | 1108598 | New Community Bus | 7738 | 7738 | CF | Y | 9th October 2013 | 12th November 2013 | Broughton Astley | Dunton Road |  | 2014-10-01 |  | Completed Sept 2014 | n/a | Completion report received 02/06/2015
| 2013/2014 | 013 R1 S106 13/14 | Dementia Harborough |  | Sensory Garden | Withdrawn | n/a |  | N/A |  |  | Market Harborough |  |  | n/a | N/A | n/a | N/A | N/A
| 2013/2014 | ROUND TWO
| 2013/2014 | 001 R2 S106 13/14 | Kibworth Grammar School | 1044822 | Improvements to Building and Exterior Fixtures | 24134 | 23284 | CF | Y | 5th March 2014 | 24th March 2014 | Kibworth Community Facilities | Warwick Road, School Road and Kibworth Court |  | 2015-03-01 | 12 months | Completed March 2015 | emailed 02/06/15 | Completed
| 2013/2014 | 002 R2 S106 13/14 | Kibworth Scouts and Guides | Scouts-116759 Guides 306016 | Extension Refurbishment of toilets and improved disabled access | 53000 | 53000 | CF | Y | 5th March 2014 | 24th March 2014 | Kibworth Community Facilities | Warwick Road |  | 01/03/2015 REVISED March 2016 | 12 months | Completed March 2016 | 2016-03-01 | Completion Report Received 08/11/2016
| 2013/2014 | 003 R2 S106 13/14 | Kibworth High School |  | Construction of all weather pitch | 44464 | 44464 | OSR | Y | 5th March 2014 | 24th March 2014 | Kibworth Community Facilities | Warwick Road |  | 2015-03-01 | 12 months | Completed March 2016 | Copmletion report filed with invoices | Completion report filed 08/11/2016
| 2013/2014 | 004 R2 S106 13/14 | Great Glen Parish Council |  | New Community Facility land purchase | 113200 | 50000 | CF | Y | 5th March 2014 | 24th March 2014 | Great Glen | Stretton Road (20,000) , Fox Pond Lane (£32,000) | Stretton Road (31/12/17) Fox Pond Lane (31/12/2017) | 2015-03-01 | 12 months | Query no completion report |  | emailed 02/06/15 | emailed 22/3/17 ENE
| 2013/2014 | 005 R2 S106 13/14 | Harborough Screen HIC |  | Provision for DDA Compliant Ramps. Funding for upgrade to toilets. Groundwork. Provision of Digital projector | 47087.12 | REFUSED |  | N/A | 5th March 2014 | 24th March 2014 | Market Harborough |  |  | n/a | N/A | N/A | N/A | N/A
| 2013/2014 | 006 R2 S106 13/14 | HDC Market Harborough |  | Improvements to Dog Walkers Path | 59000 | £34,000 Project end cost was £32,823.58 | OSR | Y | 5th March 2014 | 24th March 2014 | Market Harborough | Harborough Rubber |  | 2015-03-01 | 12 months | completed - March 2015 |  | Completion report filed 08/03/2016
| 2013/2014 | 007 R2 S106 13/14 | Market Harborough Squash and Racketball Club |  | Extension to the club including 2 glass backed courts | 60000 | 30912 | OSR | Y | 5th March 2014 | 24th March 2014 | Market Harborough | Farndon Road |  | 2015-03-01 | 12 months | completed March 2015 |  | Completed and filed 28/03/2017 ENE
| 2013/2014 | 008 R2 S106 13./14 | Welland Park Academy PTA | 1073387 | Provision of outdoor seating area | 17453 | REFUSED |  | N/A | 5th March 2014 | 24th March 2014 | Market Harborough |  |  | n/a | N/A | n/a | N/A | N/A
| 2014/2015 | ROUND ONE
| 2014/2015 | 001 R1 S016 14/15 | Fleckney Sports Centre |  | Provision of two multi sports pitches on newly acquired land | 15429 | 15429.5 | OSR | Y | 17th June 2014 | 21st July 2014 | Fleckney | Saddington Grange (£4,628.50) Former Working Men's Club (£10,800) | Saddington Grange (17.08.17) Former Working Men's Club (01.11.16) | 2016-03-01 |  | completed October 2016 |  | completion report 10/10/2016 received with invoices
| 2014/2015 | 002 R1 S016 14/15 | Swinford School |  | Outdoor Classroom and Play Equipment | 26000 | 26000 | OSR | Y | 17th June 2014 | 21st July 2014 | Swinford | Rugby Road | 17th March 2016 | 2015-09-01 |  | Completed- August 2015 |  | Completion report received August 2015
| 2014/2015 | 003 R1 S106 14/15 | Scraptoft Church |  | Provide Disabled Access | 18000 | 15000 | CF | Y | 17th June 2014 | 21st July 2014 | Scraptoft | Former De Montford Campus | 17th March 2016 | 2016-07-01 |  | Completed July 2015 |  | Report received and filed 06/15
| 2014/2015 | EXTRA ROUND
| 2014/2015 | 001 ER S106 14/15 | Thurnby Memorial Hall | 226387 | The installation of a production/ commercial kitchen and refurbishment of the existing gallery kitchen | 20260 | 20260 | CF | Y | 22nd July 2014 | 29th September 2014 | Thurnby and Bushby | Uppingham Road | 14th January 2015 | 2016-08-01 | 24 months | YES-complete |  | Completion report and invoices received 28.08.19
| 2014/2015 | 002 ER S106 14/15 | RFM Studios |  | Construction of a purpose built rehearsal room and recording studio facility | 50000 | 30000 | CF | Y | 22nd July 2014 | 29th September 2014 | Market Harborough | Tungston Batteries, Symingtons Factory, Rubber Site, Farndon Road, St Mary's | tungsten 25th Nov 2012 Rubber site 14th Jan 2016 Symingtons 10th June 2017 | 2015-09-01 | - | in progress EMAILED 20/08/2019 ene | 2015-09-01 | Follow up in October 2015
| 2014/2015 | 003 ER S106 14/15 | Broughton Astley Parish Council |  | Provision of a toilet block at the Parish Allotments | 1694 | 1694 |  | Y | 22nd July 2014 | 29th September 2014 | Broughton Astley | Coltsford Way |  | 2014-12-01 | 14 months | YES-completed March 2015 | completed March 2015 | photos and invoices received 24 June 2015
0 | 2014/2015 | 004 ER S106 14/15 | Meadowdale Primary School | XT 36023 | Community Sports Hall | 36463.8 | REFUSED |  | N/A | 22nd July 2014 | 29th September 2014 | Market Harborough |  |  | n/a | n/a | n/a | n/a | n/a
| 2014/2015 | 005 ER S106 14/15 | Kibworth Joint Recreation Committee |  | To Purchase 11.6 acres of Recreational land from LCC | 125000 | 125000 | CF AND OSR | Y | 22nd July 2014 | 29th September 2014 | Kibworth | Kibworth Cricket Club (£29,182.68 OSR) , Fleckney Road (£10,000 OSR), School Road ££35,045.50 OSR). Warwick Rd (£50,771.82 CF) | Fleckney road 29th July 2014, cricket club 7th March 2014, School Road 1st April 2016, Warwick Rd 23.12.23 | Purchase of land by October 2015 |  | Completed Nov 2015 | 01/10/2015 Purchase completed on 19th November 2015 | Completion report received 15/1/16 including a final ststement of account for the purchase. HC to confirm details
| 2014/2015 | ROUND TWO
| 2014/2015 | 001 R2 S106 14/15 | Kibworth Village Hall | 521440 | Restoration of village hall facilities | 20000 | 20000 |  | Y | 10th February 2015 | 16th March 2015 | Kibworth | Warwick Road | 23rd December 2023 | 2016-10-01 | 18 months | Completed April 2017 |  | Completion report recived 18/04/17 on file
| 2014/2015 | 002 R2 S106 14/15 | Great Glen Parish Council | n/a | Provide play equipment | 401.26 | 401.26 |  | Y | 10th February 2015 | 16th March 2015 | Great Glen | Erringtons Garage Site | 2nd May 2015 | 2015-06-01 | 2 months | completed July 2017 |  | Completion report received 09.07.19 | emailed 22/3/17 ENE, emailed 04/07/2019 AM
| 2014/2015 | 003 R2 S106 14/15 | Thurnby and Bushby Parish Council | n/a | Provide additional benches | 388.49 | 388.49 |  | Y | 10th February 2015 | 16th March 2015 | Thurnby and Bushby | Uppingham Road | 14th Jan 2015 | 2015-06-01 | 2 months | Completed March 2017 | awaiting invoices | COMPLETION REPORT and inv filed 29/03/17 ENE
| 2014/2015 | 004 R2 S106 14/15 | Meadowdale School | XT 36023 | Refurbish Toilets and Changing Rooms | 36463.8 | REFUSED |  | N/A | 10th February 2015 | 16th March 2015 | Market Harborough |  |  | n/a | n/a | n/a | n/a | n/a
| 2015/2016 | ROUND ONE
| 2015/2016 | 001 R1 S106 15/16 | Swinford Cemetery | n/a | Upgrade Burial Ground | 11484.77 | 11484.77 | OSF |  | 29th July 2015 | 7th September 2015 | Swinford | Rugby Road | 2017-12-13 | 31/6/17 | 24 months | emailed 20/08/19 ENE |  | t&c's changed - project extended | Need to request a project update MARCH 17. Emailed 29.05.18 for update & completion reports. Emailed 04/07/19 AM Emailed 20/08/19 ENE
| 2015/2016 | 002 R1 S106 15/16 | Market Harborough Town Centre | n/a | Create Footpath around Welland Park | 13200 | 13200 | OSF | Yes | 29th July 2015 | 7th September 2015 | MH | Harborough Rubber | 2016-01-14 | 2016-01-14 | 4 months | Completed April 2016 |  | Invoices on file
| 2015/2016 | 003 R1 S106 15/16 | Market Harborough Cricket Club | n/a | Refurbish and extension of cricket facilties | 17097.12 | 17097.12 | OSF | Yes | 29th July 2015 | 7th September 2015 | MH | Harborough Rubber | 2016-01-14 | 2016-01-14 | 4 months | Completed |  | Completion report 05.07.19 | emailed 22/3/17 ENE. Emailed 04/07/19 AM
| 2015/2016 | 004 R1 S106 15/16 | Shopmobility |  | Withdrawn | n/a | n/a |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
| 2015/2016 | 005 R1 S106 15/16 | Meadowdale Academy | n/a | Upgrade of toilet facilities | 8967.25 | 8967.25 | CF |  | 29th July 2015 | 7th September 2015 | MH | St Marys development | 2021-06-10 | 2016-09-30 | 12 months | n/a | n/a | n/a | school called- did not take up grant-ENE
| 2015/2016 | 006 R1 S106 15/16 | Market Harborough Baptist Church | 1132945 | Upgrade of toilet facilities | 18742.8 | 18742.8 | CF | Yes | 29th July 2015 | 7th September 2015 | MH | 32 Farndon Road (£13,299) | 2021-01-10 | 2016-09-30 | 12 months | Completed March 2015 | Still to colelct data to prove outcomes | Completion report received March 2016. Emailed to request that they collect data to prove outcomes of project.
[13 empty] | Farndon Road (5,433.80) | 2022-12-13
| 2015/2016 | 007 R1 S106 15/16 | Market Harborough Sea Cadets | n/a | Funding for minibus | up to £31,336 | 12500 | CF | Yes- 08/05/17 | 29th July 2015 | 7th September 2015 | MH | Farndon Road | 2022-12-13 | 31/09/2017 | 24 months | emailed 20/08/19 ENE
| 2015/2016 | 008 R1 S106 15/16 | Market Harborough in Bloom | n/a | Provide a water storage tank and planters - Offsite recreation infrastructure | 11092.16 | 11092.16 | OSF | Yes | 29th July 2015 | 7th September 2015 | MH | Harborough Rubber | 2016-01-14 | 2016-01-14 | 4 months | Completed March 2016 |  | Completed -report on file
| 2015/2016 | 009 R1 S106 15/16 | The Well, Kibworth | 1125246 | Upgrading Café area | 38450 | 38450 | CF | Yes | 29th July 2015 | 7th September 2015 | Kibworth | Warwick Road | 2023-12-23 | 2016-09-30 | 12 months | Completed July 2016 |  | Completion Report filed | NH to check invoices
| 2015/2016 | 010 R1 S106 15/16 | Kibworth Village Hall | 521440 | Withdrawn | 14500 | n/a |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
| 2015/2016 | 011 R1 S106 15/16 | Great Glen Community Facility | n/a | Withdrawn | 40000 | n/a |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
| 2015/16 | 012 RI S106 15/16 | Market Harborough Town Centre | n/a | Improvements to Street Furniture Town Centre Square | £11,567,89 | £11,567,89 | OSF | Yes | 29th July 2015 | 7th September 2015 | MH | Harborough Rubber (11,475.07) | 2016-01-14 | 2016-01-14 | 4 months | PROJECT COMPLETE |  | Invoices on file
[13 empty] | BP service station site (£92.91) | 2015-12-18 | 2016-01-14 | 4 months
| 2015/16 | ROUND 2
| 2015/16 | 001 R2 S106 15/16 | Gilmorton Parish Council |  | Range of outdoor equipment age 14 plus | 10273 | 10273 | OSF | Yes | 30th Nov 2015 | 11th January 2016 | Gilmorton | Goodmans Farm (£10,273) | TBC | 31st November 2017 | 18 months | emailed 20/8/19
| 2015/16 | 002 R2 S106 15/16 | Harborough Town Community Trust | 1163188 | Football and Rugby extended provisions | 230000 | 230000 | CF | YES 08/03/2018 | 30th Nov 2015 | 11th January 2016 | MH | Farndon Road (£19,676.52, £104,589, £48,033.98, £57,701.48 | 03/12/2022, 14/01/2024, 23/02/2024, 06/09/2024, | 30th April 2018 | 24 months | Completed no date |  | Update report on file 28/03/17-ENE 9.11.17 Update reporton file
| 2015/16 | 003 R2 S106 15/16 | Harborough Town Community Trust | 1163188 | Car Park Extension | 40000 | 40000 | OSF | YES 08/03/2018 | 30th Nov 2015 | 11th January 2016 | MH | Symingtons Factory (£10,002) | 2017-06-10 | 30th April 2018 | 24 months | Completed no date |  | Update report on file 28/03/17-ENE 9.11.17 Update report on file | Legal looking into spend by date - awaiting conformation
[13 empty] | St Marys Harborough Rubber (£29,998) | 2021-06-10
| 2015/16 | 004 R2 S106 15/16 | Scraptoft Village Hall |  | Village Hall Project | 188397.66 | 177525.05 | CF | Yes | 30th Nov 2015 | 11th January 2016 | Scraptoft | Former De Montford Campus (£132,273.78) | 2016-03-17 | 2016-03-17 | urgent | Completed July 2019 |  | Completion report 09.07.19 | emailed 22/3/17 ENE
[13 empty] | Beeby Road (£45,254.27) | 2020-08-01
| 2015/16 | 005 R2 S106 15/16 | Lutterworth Town Council Cemetery |  | Cemetery Turning Circle | 27500 | REFUSED |  |  | 30th Nov 2015 | 11th January 2016 | Lutterworth | n/a | n/a | n/a | n/a | n/a | n/a | Template completion report sent to Sally to complete and return incoices
521440 | 2015/16 | 006 R2 S106 15/16 | Lutterworth Town Council Skate Park |  | Lutterworth Skate Park | 15000 | REFUSED |  |  | 30th Nov 2015 | 11th January 2016 | Lutterworth | n/a | n/a | n/a | n/a | n/a | n/a | n/a
| 2015/16 | 007 R2 S106 15/16 | HDC on behalf of Welland Park |  | Welland Park signage running track signage | 4805 | 4805 | OSF | Yes | 30th Nov 2015 | 11th January 2016 | MH | Harborough Rubber Site (£4,473.54) | 2016-01-14 | 2016-01-14 |  | Completed no date? |  | project completed awaiting map ENE
[13 empty] | St Marys Harborouigh Rubber (£331.46) | 2021-06-10
ROUND 1
| 2016/17 | 001 R1 S106 16/17 | Kibworth Village Hall | 521440 | Facilities Upgrade | 11222 | £9,500 exact amount tbc | CF | nil | 26th July 2016 | 26th July 2016 | Kibworth | Warwick Road (146,948.83) Station Yard (£16,588.16) | 23/12/23 17/03/23 | 30th November 2017 | 16 months | emailed 20/08/19 |  |  | emailed 9/7/19 AM emailed 20/08/19 ENE
| 2016/17 | 002 R1 S106 16/17 | Lutterworth Town Hall | 515314 | Hall enterance upgrade | 30000 | 25000 | CF | Yes | 26th July 2016 | 26th July 2016 | Lutterwoth | Bill Crane Way (£186,123.90) | No spend by date | 31st October 2017 | 15 months | Completed Dec 2018 |  | 2018-09-16
| 2016/17 | 003 R1 S106 16/17 SEE DEF RND | Lutterworth Athletic Association |  | Changing room facility and FIFA 1 star artificial pitch | 120000 | Decision not made yet | n/a | n/a | 26th July 2016 | 20th September 2016 | Lutterworth | tbc | tbc | tbc | tbc
| 2016/17 | 004 R1 S106 16/17 SEE DEF RND | Lutterworth College |  | Changing room facilities upgrade | 58000 | Decision not made yet | n/a | n/a | 26th July 2016 | 20th September 2016 | Lutterworth | tbc | tbc | tbc | tbc
| 2016/17 | 005 R1 S106 16/17 | MHRUFC |  | Floodlights and draining upgrage | 79800 | 79800 | OSR | Yes | 26th July 2016 | 26th July 2016 | MH | St Marys Development (£2,266.15) Lathkill Street (£110,852.32) | 10/06/2021 Lathkill tbc | 30th November 2017 | 16 months | completion due 10/06/2021
| 2016/17 | 006 R1 S106 16/17 | Kibworth Joint recreation Committee |  | Carpark upgrade and installation of bins/benches and notice board | 18507.93 | 18507.93 | OSF | Yes | 26th July 2016 | 26th July 2016 | Kibworth | 9 Weir Road (£57,187.23) | 2020-04-16 | 31st August 2017 | 14 months | Completed no date- | Completion report 10.07.19 | emailed for report 09.07.19 AM
| 2016/17 | 007 R1 S106 16/17 SEE DEF RND | Kibworth Library Access Upgrade |  | Kibworth library access upgrade | 8311 | Decision not made yet | n/a | n/a | 26th July 2016 | 20th September 2016 | Kibworth | tbc | tbc | tbc | tbc
| 2016/17 | Deffered Round
| 2016/17 | 001 R1 Def S106 | Lutterworth Athletic Association |  | Changing room facility and FIFA 1 star artificial pitch | 120000 | NO RESUBMISSION MADE | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
| 2016/17 | 002 Def S106 | Lutterworth College |  | Changing room facilities | 8700 | 3625 | CF |  | 26th July 2016 | 20th September 2016 | Lutterworth | Bill Crane Way (£161,123.90) | No spend by |  | 24 months | emailed 20/08/2019 ENE
| 2016/17 | 003 R1 Def S106 | Kibworth Beauchamp Parish Council |  | Kibworth library access upgrade | 8311 | 6588.16 | CF | No | 26th July 2016 | 20th September 2016 | kibworth Beauchamp | Station Yard (£6,588.16) | 2023-03-17 |  | 12 months | emailed 20/08/2019 ENE
| 2016/17 | 004 R1 Def S106 | Broughton Astely Parish Council |  | Consultancy Work | 42000 / 40,000 | 40000 |  | PAID | 26th July 2016 | 20th September 2016 | Broughton Astely | 136 Loughborough Road (£52,692.30) |  |  | 18 months | Completed July 2018 | Completion report 10.09.18
| 2016/17 | 005 R1 Def S106 | Broughton Astely Parish Council |  | Multi Games Area | 141744.71 | Refused | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
| 2016/17 | 006 R1 Def S106 | Scraptoft Parish Council |  | Village Hall Project | 25239.98 | £25.239.98 | CF | PAID | 26th July 2016 | 20th September 2016 | Scraptoft | Beeby Road | 2020-08-01 |  |  | due for completion 1/08/2020
| Year | Project No | Applicant | Applicant Charity No | Project Name | Amount Requested | Decision | CF or OSR or Play (reason for spend) | Pd? | Member Grant Panel Date | Exec Decision Date | Parish Area | Development/s Funding Project | Spend by date for allocated money | Date to be completed by as per T and Cs | Total time given to deliver project | Project Completed? ….. | Projected-Date-For-Completion…. | Monitoring Report Received (date) | Additional Monitoring Notes
| 2017/18 | 001 R1 S106 | 1st Bowdens Scouts | 521767 | Demolition and recontruciton of scout hut | 64505 | Refused | n/a | n/a |  | 11th May 2017 | n/a | n/a | n/a | n/a | n/a
| 2017/18 | 003 R1 S106 | Kibworth Joint Burial Committee |  | Refurbishment of memorials | 4486.91 | Refused | n/a | n/a |  | 11th May 2017 | n/a | n/a | n/a | n/a | n/a
| 2017/18 | 004 R1 S106 | Fleckney Sports Centre |  | Resurfacing of the all weather pitch | 23000 | 23000 | Sports Facility upgrade | Paid |  | 11th May 2017 | Fleckney | £15,946.99 Leicester Road, Fleckney | 2021-08-07 | 31st December 2017 | 7 months | Completed Oct 2017
| 2017/18 | 006 R1 S106 | Fleckney Sports Centre |  | Upgrade of sports centre acoustics | 4000 | 4000 | Sports Facility upgrade | paid 29/09/17 |  | 11th May 2017 | Fleckney | £15,946.99 Leicester Road, Fleckney | 2021-08-07 | 31st December 2017 | 7 months | emailed 20/08/2019 |  |  | chased up again 13.02.2020 via email
| 2017/18 | 007 R1 S106 | Gilmorton Village Hall |  | Village Hall upgrade of heating system | 6949 | 5212 | Community Facility upgrade | paid |  | 11th May 2017 |  | Goodmans Farm Gilmorton | 2021-08-07 | 31st August 2017 | 3 months | Yes, awaiting report 29.01.19 |  |  | chased up again 13.02.2020 via email
| 2017/18 | 001 R1 S106 | Fleckney Allotment Association |  | New water provision resource | 680 | 510 | Allotment service provision upgrades | PAID |  | 11th May 2017 | Fleckney | £1382.98 Leicester Road, Fleckney | 2021-08-07 | 31st July 2017 | 2 months | Yes | 2018-02-20
| 2017/18 | 001 R1 S106 | Fleckney Baptist Pre-School | 1154011 | Installation of new fence and gate | 5705.4 | Refused | n/a | n/a |  | 11th May 2017 | n/a | n/a | n/a | n/a | n/a
| 2017/18 | 010 R1 S106 | Fleckney Silver Band |  | Car park matting | 4323 | Refused | n/a | n/a |  | 11th May 2017 | n/a | n/a | n/a | n/a | n/a
| 2017/18 | 011 R1 S106 | Fleckney Cricket Club |  | Container for use as a changing room at recreation ground | 6450 | Refused | n/a | n/a |  | 11th May 2017 | n/a | n/a | n/a | n/a | n/a
| 2017/18 | 012 R1 S106 | Fleckney Village Hall | 521418 | Village Hall upgrade of heating system | 15000 | 7973 | Community Facility upgrade | PAID |  | 11th May 2017 | Fleckney | £15,946.99 Leicester Road, Fleckney | 2021-08-07 | 2018-06-30 | 13 months | Completed June 2018 | 22.06.18
| 2017/18 | 013 R1 S106 | Lutterworth FC |  | Remodelling of the club house and toilet upgrade | 22500 | 22500 | Community Facility upgrade | PAID |  | 11th May 2017 | Lutterworth | £157,498.90 Bill Crane Way, Lutterworth | No spend by date | 31st October 2017 | 5 months | Yes completion report received 28/07/19, awaiting invoice
| 2017/18 | 015 R1 S106 | St. Dionysius Church Hall | 1133101 | New energy efficient heating system and lighting and a new non-slip floor | 12801 | 10000 | Community Facility upgrade | PAID |  | 11th May 2017 | Market Harborough | £31,731.44 Farndon Road, Market Harborough | 2024-09-06 | 30th September 2017 | 4 months | Completed 11/9/17 | 2017-09-30 | 2017-09-11
| 2017/18 | 016 R1 S106 | St Nicholas Church Fleckney |  | Ground clearance for 24 burial plots | 2398 | 1800 | Cemetery provision | PAID |  | 11th May 2017 | Fleckney | £5,754.68 Leicester Road, Fleckney | 2021-08-07 | 31st October 2017 | 5 months | completed-26/03/18 | 23.03.18
| 2017/18 | 018 R1 S106 | Thurnby and Bushby parish Council |  | Provision of Multi Games Area (MUGA) | 46893 | 46893 | Offsite recreation provision | PAID |  | 26th Janusry | Thurby and Bushby | 46,893 919 Uppingham Road | 2017-04-14 | 30th Septemeber 2017 - extension to Spring 2018 | 8 months (extd to Spring 2018) | Thurnby PC will complete this project in searly spring due to some additional work in relation to slabbing around the muga. S106 group confirmed the work was necessary. The slight underpayment will part pay for this and remainder will come from the PC. | Project completed awaiting report | spoke to Sue 04/07/19. she has completion report and will fill in asap emailed 20/08/2019 ENE | Chased up again 13/02/2020 via email and phone message.
| 2017/18 | 019 R1 S106 | The Enterprise Centre | 1168564 | Convert toilet into a fully disabled access toilet | 11970 | Refused | n/a | n/a |  | 11th May 2017 | n/a | n/a | n/a | n/a | n/a
| 2017/18 | 020 R1 S106 | Fleckney Silver Band |  | Upgrade floor and wall insulation | 8756.09 | 7973 | CF | PAID | n/a | 11th May 2017 | Fleckney | £15,946.99 Leicester Road, Fleckney | 2021-08-07 | 30th November 2017 | 6 months | COMPLETED 3108/17 | 2017-11-30 | 2017-08-31
| Year | Project No | Applicant | Applicant Charity No | Brief Outline of Proposal | Amount Requested | Decision | CF or OSR or Play | Pd? | Member Grant Panel Date | Exec Decision Date | Parish Area | Development/s Funding Project | Spend by date for allocated money | Date to be completed by as per T and Cs | Total time given to deliver project | Project Completed? ….. | Projected-Date-For-Completion…. | Monitoring Report Received (date) | Additional Monitoring Notes
| 2017/18 | 001 R2 S106 | Fleckney Parish Council |  | Spinney Wood land Pro ject | 3704.9 | 3704.9 | Children’s Play Area and Parks and Gardens provision and upgrade | PAID | n/a | 5th October 2017 | Fleckney | Leicester Road Fleckney | 7.8.21 | 31st March 2018 | 6 months | Completed 18/04/2018 |  | Completed report 19.04.18
| 2017/18 | 002 R2 S106 | Fleckney Parish Council |  | Offsite recreational furniture provision | 2552.49 | 2552.49 | Parks and Gardens provision and upgrade | PAID | n/a | 5th October 2017 | Fleckney | Leicester Road Fleckney | 7.8.21 | 31st March 2018 | 6 months | Completed 19/04/2018 |  | Completed report 23.04.18
| 2017/18 | 003 R2 S106 | Fleckney Parish Council |  | Provision of permanent outdoor table tennis facilities | 1921.46 | 1921.46 | Sports Facilities provision | PAID | n/a | 5th October 2017 | Fleckney | Leicester Road Fleckney | 7.8.21 | 31st March 2018 | 6 months | Completed 18/04/2018 |  | Completed report 19.04.18
| 2017/18 | 004 R2 S106 | 1st Bowdens Scouts |  | Demolisiona nd rebuild of the scout hut | 64.505 | refused - application deferred | n/a | n/a | n/a | 5th October 2017 | n/a
| 2017/18 | 005 R2 S106 | Kibworth Tennis Club |  | Demolisiona nd rebuild of the tennis club | 50000 | 50000 | Provision of New Community Facility | PAID | n/a | 5th October 2017 | Kibworth | Warwick Road | 23.12.23 | 30th Jan 2019 | 18 months | Completed |  | Completion report 05.09.19 | Plaque offered 05.09.19
| 2017/18 | 006 R2 S106 | Lutterworth Town Council |  | Provision of cemetery storage | 9315 | 9315 | Cemetery Service provision | PAID | n/a | 5th October 2017 | Lutterworth | Bill Crane Way | no spend by date | 30th April 2018 | 6 months | Completed |  | Completed report 02.09.19
| 2017/18 | 007 R2 S106 | Lutterworth Town council |  | Provision of Columbarium | 3900 | 3900 | Cemetery Service provision | PAID | n/a | 5th October 2017 | Lutterworth | Bill Crane Way | no spend by date | 30th April 2018 | 6 months | Completed 24/2/2018 | 12.03.18 | completed report 12.03.18
| 2017/18 | 008 R2 S106 | Lutterworth Town Council |  | Provision of Memorial park gardens lights | 2350 | 2350 | Parks and gardens provision | PAID | n/a | 5th October 2017 | Lutterworth | Land East Side Leicester Road | 11.05.2022 | 30th April 2018 | 6 months | Completed April 2018 |  | Completed report 10.08.16
| 2017/18 | DEF R2 S106 | Great Glen Parish Council |  | Extension of changing rooms | 63200 | 63200 | Communities facilities | PAID | n/a | 20th July 2017 | Great Glen | Fox pond Lane | 31.10.2017 | 31st December 2017 |  | Completed 31/07/18 | 31.12.17 | completed report 31.07.18
| 2017/18 | 009 R2 S106 | HDC for Welland Park |  | Wheelchair and Pushchair Accessible Path | 1470.6 | 1470.6 | Upgrade of Market Harborough offsite recreation | PAID | n/a | 5th October 2017 | Market Harborough | St Mary's Development | 10.06.2021 | 30th April 2018 | 6 months | Completed NO DATE
| Year | Project No | Applicant | Applicant Charity No | Brief Outline of Proposal | Amount Requested | Decision | CF or OSR or Play | Pd? | Member Grant Panel Date | Exec Decision Date | Parish Area | Development/s Funding Project | Spend by date for allocated money | Date to be completed by as per T and Cs | Total time given to deliver project | Project Completed? ….. | Projected-Date-For-Completion…. | Monitoring Report Received (date) | Additional Monitoring Notes
| 2017/18 | 001 R3 S106 | Lutterworth Town Council |  | Build new allotment site | 18146.28 | 18146.28 | Allotment provision | Paid | n/a | 23rd January 2018 | Lutterworth | Leicester Road | 2022-05-01 | 2020-01-31 | 24 months
| 2017/18 | 002 R3 S106 | Scraptoft Parish Council |  | Internal fixtures and fittings for Hub | 2490 | 11875 | Community Facility upgrade | paid £2490 and £9385 | n/a | 23rd January 2018 | Scraptoft | Station Lane | 2018-12-01 | 2019-01-31 | 12 months | Completed 11/02/19 | 28.02.19
| 2017/18 | 003 R3 S106 | Boughton Astley Parish Council |  | New heating system for The Cottage | 3293.65 | 3293.65 | Community Facility upgrade | No | n/a | 23rd January 2018 | Broughton Astley | Dunton Road 2005 | 2019-04-01 | 2018-07-31 | 6 months | Defered to later round as trouble with Installer
| 2017/18 | 001 R4 S106 | Dunton and Broughton FC |  | Improving access and quality to car park | 5000 | Allocated from a different funding source | Off site rec facilities |  | n/a | 23rd January 2018 | Dunton | Dunton Road 2005 | n/a | n/a | n/a | n/a
| 2017/18 | 005 R3 S106 | Broughton Astley Cricket Club |  | Install wicket covers | 4650 | 4650 | Offsite recreation upgrade | PAID | n/a | 23rd January 2018 | Broughton Astley | Dunton Road 2005 | 2019-07-01 | 2018-07-31 | 6 months | Yes | 16.10.18 | emailed 15.01.19
| 2017/18 | 006 R3 S106 | Market Harborough in Bloom Volunteers |  | Self watering barrels and tier planter | 3961.4 | 3961.4 | Upgrade of Market Harborough offsite recreation | PAID | n/a | 23rd January 2018 | Market Harborough | St Marys Development | 2021-06-01 | 2019-01-31 | 12 months | Completed 24/01/2019 | 29.01.18
| 2017/18 | 007 R3 S106 | St Dionysius Community Hall |  | New sound system | 1202 | 1202 | Community Facility upgrade | PAID | n/a | 23rd January 2018 | Market Harborough | St Marys Development | 2021-06-01 | 2018-07-31 | 6 months | Completed 08/03/18 | 22.02.18 | completed report 22.02.18
| Year | Project No | Applicant | Applicant Charity No | Brief Outline of Proposal | Amount Requested | Decision | CF or OSR or Play | pd? | Member Grant Panel Date | Exec Decision Date | Parish Area | Development/s Funding Project | Spend by date for allocated money | Date to be completed by as per T and Cs | Total time given to deliver project | Project Completed? ….. | Projected-Date-For-Completion…. | Monitoring Report Received (date) | Additional Monitoring Notes
| 2018/19 | 001 R1 S106 | Market Harborough Baptist Church | 1132945 | Upgrade community hall facility | 128378 | 45000 | Community Facility upgrade | PAID | n/a | 25th April 2018 | Market Harborough | Farndon Road | 2024-10-06 | 2019-11-01 |  | EMAILED 20/08/2019 ENE
| 2018/19 | 002 R1 S106 | Market Harborough Unit of Sea Cadets Corps |  | withdrawn |  |  |  | n/a | n/a | 25th April 2018 | Market Harborough |  |  | n/a
| 2018/19 | 003 R1 S106 | Fleckney Parish Council |  | Installation of new fence and viewing platform decking | 7601.84 | 2070.53 | OSR Parks and Gardens | No | n/a | 25th April 2018 | Fleckney | Leicester Road | 2021-08-07 |  |  | awaiting outcome of area ownership
| 2018/19 | 004 R1 S106 | Aylestone St James Rugby |  | New roof, photo voltaics, internal decoration | 10000 | Refused - no funding available |  | n/a | n/a | 25th April 2018
| 2018/19 | 005 R1 S106 | Lutterworth FC |  | New clubhouse at Lutterworth School, improve 3 grass pitches, 1st team pitch with hard standing, covered seats, floodlights | 120000 | 50000 | Community Facilities / Sports recreation | No | n/a | 25th April 2018 | Lutterworth | Leicester Road | 11/085/2022 |  |  | Project fell through. £50k to be returned
| 2018/19 | 006 R1 S106 | The Cube | 1110510 | Automated door opening device, External office, outdoor classroom, furnishing and fittings | 13250 | Defer decision | Community facilities | n/a | n/a | 25th April 2018 | Market Harborough
| Year | Project No | Applicant | Applicant Charity No | Brief Outline of Proposal | Amount Requested | Decision | CF or OSR or Play | pd? | Member Grant Panel Date | Exec Decision Date | Parish Area | Development/s Funding Project | Spend by date for allocated money | Date to be completed by as per T and Cs | Total time given to deliver project | Project Completed? ….. | Projected-Date-For-Completion…. | Monitoring Report Received (date) | Additional Monitoring Notes
| 2018/19 | 001 R2 S106 | Welland Park Academy |  | Refurbishment of Sports Hall facilities | 12000 | 12000 | Community facilities | PAID | n/a | 1st Nov 2018 | Market Harborough | Fardon Rd, Lubenham Hill, St Marys Dev | 2024, No SBD, 04/06/21 | 31st March 2019 | 6 months | EMAILED 20/08/2019 ENE
| 2018/19 | 002 R2 S106 | Houghton Village Hall | 521432 | Extension of Village Hall | 27500 | 27500 | Community facilities | PAID | n/a | 1st Nov 2018 | Houghton | Land off Winkley Rd, Uppingham Rd | No SBD, 17/07/25 | 31st March 2019 | 6 months | EMAILED 20/08/2019 ENE
| 2018/19 | 003 R2 S106 | Kibworth Joint Burial Committee |  | New footpath linking to existing footpaths | 4520 | 4520 | Offside rec | PAID | n/a | 1st Nov 2018 | Kibworth | Wistow Rd | 2022-08-25 | 31st March 2019 | 6 months | Yes | Completion report 06.11.19
| 2018/19 | 004 R2 S106 | Houghton Bowls Club |  | Complete overhaul of main green | 10000 | TBC once funding is available | Offsite rec | n/a | n/a | 1st Nov 2018 | Houghton | No funding at present | n/a | n/a
| 2018/19 | 005 R2 S106 | Broughton Astley Off site |  | Car parking for Sports facilities | 132618.37 | Deferred to R3 | Offsite rec | n/a | n/a | 1st Nov 2018 | Broughton Astley | Dunton Rd | 2019-04-07
| 2018/19 | 006 R2 S106 | Broughton Astley Consultation |  | Stage 2 of Consultancy and design for Community facility to include Leisure and Medical Centre | 12692.3 | 12692.3 | Community facilities/ consultancy | PAID | n/a | 1st Nov 2018 | Broughton Astley | Jelson off Broughton Way | No SBD | 31st March 2019 | 6 months | Yes | Completion report 23.05.19
| 2018/19 | 007 R2 S106 | Lutterworth Town Estates Charity |  | New building to benefit Lutterworth Museum | 150000 | Deferred | Community facilities | n/a | n/a | 1st Nov 2018 | Lutterworth | Bill Crane way, Leicester Rd, Gilmorton Rd | n/a | n/a
| 2018/19 | 008 R2 S106 | Fleckney Village Hall | 521418 | Refurbishment of Village Hall | 43207 | TBC once funding is available | Community facilities | n/a | n/a | 1st Nov 2018 | Fleckney | No funding available | n/a | n/a
| 2018/19 | 009 R2 S106 | MH Tennis Club |  | New Clubhouse floodlighting | 100882 | 100882 | Community facilities/Offsite rec | No | n/a | 1st Nov 2018 | Market Harborough | Fernie Stables, Welham Rd, MH North of Lubenham Hill, MH Farndon Rd, MH St Marys Dev, Peaker Park, Overstone House | 30/03/20, 01/03/23, No SBD, 23/02/24, 04/06/21 | 31st March 2019 | 6 months | Needs to be taken back to the panel and allocate funds from Peaker Park/ Overstone House. 1. Airfield Road, Mkt Harborough £79,896.00 11/00112/OUT 2. Northampton Road, Mkt Harborough £14,767.00 no planning reference quoted – refurbish leisure centre 3. Overstone House, Mkt Harborough £34,857.00 no planning reference quoted 4. Peaker Park, Mkt Harborough £21,315.00 17/01483/FULL 5. Lubenham Hill £47,333 12/00044/FUL
| 2018/19 | 010 R2 S106 | Broughton Astley Energy |  | New heating system for The Cottage | 1810.5 | 1810.5 | Community facilities | PAID | n/a | 1st Nov 2018 | Broughton Astley | Dunton Rd | 2019-04-07 | 7th April 2019 | 6 months | Yes | Completion report 19/12/2018
| 2018/19 | 011 R2 S106 | Bowden Cricket Club |  | Outdoor practice net facility with artificial cricket wicket | 13000 | 13000 | Off site rec | PAID | n/a | 1st Nov 2018 | Great Bowden | Fernie Stables | 2020-03-03 | 31st March 2019 | 6 months | Yes | Completion report 22.08.19
| 2018/19 | 012 R2 S106 | Lutterworth Wellbeing Centre | 1120025 | Major alteration to Estates House/Lutterworth College Site to include kitchen, walls, floors and conservatory | 67600 | Deferred | Community facilities | Paid | n/a | 1st Nov 2018 | Lutterworth | Bill Crane way, Leicester Rd, Gilmorton Rd | n/a | n/a
| 2018/19 | 013 R2 S106 | The Well | 1125246 | Rebranding, soundproofing, New shop front, | 9977 | 4089.99 | Community facilities | PAID | n/a | 1st Nov 2018 | Kibworth | Longbreach Rd, Warwick Rd, Station yard, Fleckney Rd, SE of Warwick Rd | 27/05/23, 21/12/23, 17/03/23, 17/03/23, 21/12/24, 24/04/23 | 31st March 2019 | 6 months | Emailed 20/08/2019 ENE |  | setback with project due to complete Feb 2020
| 2018/19 | 014 R2 S106 | Hart of Fleckney Bowl |  | TBC | TBC | Deferred | Deferred | TBC | n/a | 1st Nov 2018 | Fleckney
| Year | Project No | Applicant | Applicant Charity No | Brief Outline of Proposal | Amount Requested | Decision | CF or OSR or Play | pd? | Member Grant Panel Date | Exec Decision Date | Parish Area | Development/s Funding Project | Spend by date for allocated money | Date to be completed by as per T and Cs | Total time given to deliver project | Project Completed? ….. | Projected-Date-For-Completion…. | Monitoring Report Received (date) | Additional Monitoring Notes
| 2018/19 | 005 def R2 S106 EXORD | Broughton Astley Off site |  | Car parking for Sports facilities | 132618.37 | 132618.37 | Offsite rec | PAID | n/a | 5th Dec 2018 | Broughton Astley | Dunton Rd | 2019-04-07 | 2019-12-01 | 1 year
| Year | Project No | Applicant | Applicant Charity No | Brief Outline of Proposal | Amount Requested | Decision | CF or OSR or Play | pd? | Member Grant Panel Date | Exec Decision Date | Parish Area | Development/s Funding Project | Spend by date for allocated money | Date to be completed by as per T and Cs | Total time given to deliver project | Project Completed? ….. | Projected-Date-For-Completion…. | Monitoring Report Received (date) | Additional Monitoring Notes
| 2018/19 | Transfer round from CGF | Fleckney Silver Band |  | Fencing and creating an outdoor covered patio space | 5000 | 3500 | OSR Parks and Gardens |  | n/a | 22nd Jan 2019 | Fleckney | Leicester Road Fleckney | 2021-08-07 | 31st March 2020 | 1 year |  |  |  | Update needed
| 2018/19 | Transfer round from CGF | Fleckney Parish Council |  | New tree orchard in unused area of park | 1400 | 1130 | OSR Parks and Gardens |  | n/a | 22nd Jan 2019 | Fleckney | Leicester Road Fleckney | 2021-08-07 | 31st March 2020 | 1 year |  |  |  | Update needed
| Year | Project No | Applicant | Applicant Charity No | Brief Outline of Proposal | Amount Requested | Decision | CF or OSR or Play | pd? | Member Grant Panel Date | Exec Decision Date | Parish Area | Development/s Funding Project | Spend by date for allocated money | Date to be completed by as per T and Cs | Total time given to deliver project | Project Completed? ….. | Projected-Date-For-Completion…. | Monitoring Report Received (date) | Additional Monitoring Notes
| 2018/19 | S106 R2 Extra 18/19 EXORD | Lutterworth Wellbeing Centre |  | Major alteration to Estates House/Lutterworth College Site to include kitchen, walls, floors and conservatory | £56,000 tbc | £56,000 tbc | CF | Deferred (see below) | n/a | 14th March 2019 | Lutterworth | Bill Crane Way Gilmorton | no SBD 29.03.23 | 30th Feb 2020 | 6 months |  |  |  | Delay in finalising the lease . Project due to start 2020
| Year | Project No | Applicant | Applicant Charity No | Brief Outline of Proposal | Amount Requested | Decision | CF or OSR or Play | pd? | Member Grant Panel Date | Exec Decision Date | Parish Area | Development/s Funding Project | Spend by date for allocated money | Date to be completed by as per T and Cs | Total time given to deliver project | Project Completed? ….. | Projected-Date-For-Completion…. | Monitoring Report Received (date) | Additional Monitoring Notes
| 2019/20 | S106 Exord 19/20 | Lutterworth Wellbeing Centre (ref S106 R2 Extra 18/19 | 12176266 | Major alteration to Estates House/Lutterworth College Site to include kitchen, walls, floors and conservatory | 57967.2 | 57967.2 | CF | Y | n/a | 30th July 2019 | Lutterworth | Bill Crane Way Gilmorton Road | No SBD 29.03.23 | 31st Feb 2020 | 6 month | project delayed until Feb 2020
| Year | Project No | Applicant | Applicant Charity No | Brief Outline of Proposal | Amount Requested | Decision | CF or OSR or Play | pd? | Member Grant Panel Date | Exec Decision Date | Parish Area | Development/s Funding Project | Spend by date for allocated money | Date to be completed by as per T and Cs | Total time given to deliver project | Project Completed? ….. | Projected-Date-For-Completion…. | Monitoring Report Received (date) | Additional Monitoring Notes
| 2019/20 | 001 R1 S106 2019/20 | Broughton Astley Parish Council |  | Community Leisure facility, medical centre, car parking, 3G artificial pitch and infrastructure | 50141 | 50141 | CF |  | n/a | 3rd October 2019 | Broughton Astley | Dunton Road | 11.04.22 | 2020-03-01 | 9 months
| 2019/20 | 002 R1 S106 19/20 | Robert Smyth Academy |  | Full size floodlit sand dressed artificial grass pitch for the Hockey Club and a multitude of other sports | 370000 | 370000 | Outdoor Sports Contribution |  | n/a | 3rd October 2019 | M.Harborough | Lathkill Street Lubenham Hill Angell Drive | 18.01.21 No SBD TBC | 2020-07-01 | 9 months | possible delay in project
| 2019/20 | 003 R1 S106 19/20 | Lutterworth Town Estates |  | Major alteration to Estates House/Lutterworth College Site to include kitchen, walls, floors and conservatory | 150000 | Deferred | CF | n/a | n/a | 3rd October 2019 | Lutterworth
| 2019/20 | 004 R1 S106 19/20 | Fleckney Village Hall |  | Washroom Refurbishment Project | 48555.5 | 48555.5 | CF | Paid | n/a | 3rd October 2019 | Fleckney | Land off Fleckney Road/Persimmon | 26.06.24 | 2020-10-01 | 6 months
| 2019/20 | 005 R1 S106 19/20 | Lutterworth Tennis Club |  | Tennis Dome to cover 2 courts to provide all year round play | 120000 | 120000 | Sports Facilities provision/CF for indoor sports |  | n/a | 3rd October 2019 | Lutterworth | Gilmorton Road Leicester Road | 23.03.23 11.05.22 | 2020-10-01 | 12 months
| 2019/20 | 006 R1 S106 19/20 | Houghton Bowls Club |  | Club Renovation and Extension of Bowling Green | 37000 | 37000 | Sports facilities | Paid | n/a | 3rd October 2019 | Houghton | Land of Winckley Close | No SBD | 2020-01-01 | 3 months
| 2019/20 | 007 R1 S106 19/20 | Aylestone St James Rugby |  | Development of roof space, changing rooms and kitchen | 20000 | Deferred | CF | n/a | n/a | 3rd October 2019 | Scraptoft
| 2019/20 | 008 R1 S106 19/20 | Lutterworth Cemetery |  | Erect iron fencing to front of cemetery | 12980 | Deferred | Cemeteries | n/a | n/a | 3rd October 2019 | Lutterworth
| 2019/20 | 009 R1 S106 19/20 | Lutterworth Town FC |  | Additional changing rooms | 18575 | Deferred | FSIF | n/a | n/a | 3rd October 2019 | Lutterworth
| 2019/20 | 010 R1 S106 19/20 | Fleckney Village Hall |  | Refurbishment of roof membranes, guttering, fascias and downpipes | 11940 | Refused | CF | n/a | n/a | 3rd October 2019 | Fleckney
| 2019/20 | 011 R1 S106 19/20 | Bowman of Great Glen |  | New Clubhouse and indoor range | 65000 | Deferred until March | CF | n/a | n/a | 3rd October 2019 | Great Glen
| 2019/20 | 012 R1 S106 19/20 | Kibworth Joint Recreation Committee |  | Replace fence with steel railings and gates to improve safety within play area | 18750.96 | 18750.96 | OSR Parks and Gardens | Paid | n/a | 3rd October 2019 | Kibworth | 9 Weir Road | 01.04.20 | 2020-03-01 | 6 months
| Year | Project No | Applicant | Applicant Charity No | Brief Outline of Proposal | Amount Requested | Decision | CF or OSR or Play | pd? | Member Grant Panel Date | Exec Decision Date | Parish Area | Development/s Funding Project | Spend by date for allocated money | Date to be completed by as per T and Cs | Total time given to deliver project | Project Completed? ….. | Projected-Date-For-Completion…. | Monitoring Report Received (date) | Additional Monitoring Notes
| 2019/20 | 001 R1 DEF | Robert Smyth Academy |  | Phase 3. Tennis Court and Netball Court | 50000 | 50000 | SF |  | n/a | 29th January 2020 | M. Harborough | Burnmill Farm | 2024-12-16 |  | 12 months
| 2019/20 | 002 R1 DEF | Aylestone St James Rugby |  | Development of roof space, changing rooms and kitchen for the club house | 20000 | 20000 | CF |  | n/a | 29th January 2020 | Scraptoft | Pulford Drive |  | 2021-08-01 | 12 months
| 2019/20 | 003 R1 DEF | Lutterworth Town Council |  | Iron fencing to surround Lutterworth Cemetery | 18254 | 18254 | Cemetries |  | n/a | 29th January 2020 | Lutterworth | Bill Crane Way | No SBD |  | 6 months
| 2019/20 | 004 R1 DEF | Kibworth Cricket Club |  | Develp shadow pavilion for ladies and junior cricket | 60000 | 60000 | OSR/SF |  | n/a | 29th January 2020 | Kibworth | Longbreach Development/ 4 Fleckney Road | 01/04/2024 21/12/2024 |  | 12 months
| 2019/20 | 005 R1 DEF | The Hub Scraptoft |  | Extension to Community Hub | 536108 | 536108 | CF |  | n/a | 29th January 2020 | Scraptoft | Beeby Road | 2025-07-13 |  | 12 months
| 2019/20 | 006 R1 DEF | Kibworth Joint Recreation Committee |  | Multi Use Games Area | 26860 | 26860 | OSR |  | n/a | 29th January 2020 | Kibworth | 9 Weir Road 4 Fleckney Road | April 2020 21/12/2024 |  | 6 months

## Compatibility Report
Compatibility Report for MASTER S106 Grant Applications Record - 06082018.xls
Run on 19/12/2018 08:42
The following features in this workbook are not supported by earlier versions of Excel. These features may be lost or degraded when opening this workbook in an earlier version of Excel or if you save this workbook in an earlier file format.
Minor loss of fidelity | # of occurrences | Version
Some cells or styles in this workbook contain formatting that is not supported by the selected file format. These formats will be converted to the closest format available. | 283 | Excel 97-2003

## Compatibility Report (1)
Compatibility Report for Website - MASTER S106 Grant Applications Record - 13022020.xls
Run on 13/02/2020 13:31
If the workbook is saved in an earlier file format or opened in an earlier version of Microsoft Excel, the listed features will not be available.
Minor loss of fidelity | # of occurrences | Version
Some cells or styles in this workbook contain formatting that is not supported by the selected file format. These formats will be converted to the closest format available. | 262 | Excel 97-2003