## LP traj
Harborough District Council Local Plan Housing Allocations 2020-2041
|  | Settlement | Site Allocation | Application Number | 2025/26 | 2026/27 | 2027/28 | 2028/29 | 2029/30 | 2030/31 | 2031/32 | 2032/33 | 2033/34 | 2034/35 | 2035/36 | 2036/37 | 2037/38 | 2038/39 | 2039/40 | 2040/41 | 2041/42 | 2042/43 | 2043/44 | 2044/45 | Total
Harborough District Council (HDC) Local Plan Allocations | Leicester Urban Area | Thurnby/Bushby | TB1: Land north of the A47, east of Zouche Way. | 25/01615 /OUT ** | 2028/29: 50; 2029/30: 50; 2030/31: 25 | 125
|  |  | 125 Homes | 130 Homes
|  | Scraptoft | S1: Land between Scraptoft & Bushby | 26/00289/OUT ** | 2030/31: 50; 2031/32: 100; 2032/33: 100; 2033/34: 100; 2034/35: 100; 2035/36: 100; 2036/37: 100; 2037/38: 100; 2038/39: 100; 2039/40: 100 | 950
|  |  | 950 Homes | 950 homes
|  | Scraptoft | S2: Land East of Beeby Road | 25/00767 /OUT ** | 2028/29: 50; 2029/30: 50; 2030/31: 50; 2031/32: 25 | 175
|  |  | 175 Homes | 200 Homes
|  | Oadby | OA1: Land South of Gartree Road **** | [9 empty] | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 485 | 485 | 485 | 495 | 3150
3,150 homes
| Market Towns | Lutterworth | L1: Land off Leicester Road | 26/00447 /OUT ** | 2028/29: 50; 2029/30: 50; 2030/31: 50; 2031/32: 50; 2032/33: 30 | 230
|  |  | 230 Homes | 235 Homes
|  | Lutterworth | L2: Land at M1 Junction 20/Swinford Road | 25/00746 /OUT * | 2026/27: 40; 2027/28: 50 | 90
|  |  | 90 Homes | 90 Homes
|  | Market Harborough | MH1: Land east of Leicester Road and south of Grand Union canal |  | 2028/29: 50; 2029/30: 50; 2030/31: 50; 2031/32: 50; 2032/33: 50 | 250
250 Homes
|  | Market Harborough | MH2: East of Market Harborough Road | 25/00736/SCP (EIA Scoping) | [6 empty] | 30 | 50 | 120 | 120 | 130 | 130 | 160 | 160 | 120 | 90 | 90 | 90 | 90 | 70 | 1450
850 Homes
|  | Market Harborough | MH3: Land south of Gallow Field Road
600 Homes
| Large Villages | Broughton Astley | BA1: Land off Frolesworth Road | 26/00480 /OUT ** | 2030/31: 40; 2031/32: 80; 2032/33: 80; 2033/34: 80; 2034/35: 80; 2035/36: 80; 2036/37: 35 | 475
|  |  | 475 Homes | 550 Homes
|  | Fleckney | F1: Land north of Kilby Road and west of Longgrey | 25/00515 /OUT * | 2028/29: 50; 2029/30: 50; 2030/31: 50 | 150
|  |  | 150 Homes | 170 Homes
|  | Great Glen | GG1: Land to the North of London Road and east of Leicester Grammar School | 25/01467 /OUT ** | 2030/31: 40; 2031/32: 80; 2032/33: 80; 2033/34: 80; 2034/35: 80; 2035/36: 40 | 400
|  |  | 400 homes | 450 homes
|  | Kibworth | K1: Land west of Warwick Road |  | 2030/31: 40; 2031/32: 80; 2032/33: 80; 2033/34: 80; 2034/35: 80; 2035/36: 80; 2036/37: 35 | 475
475 Homes
| Medium Villages | Billesdon | B1: Land at Gaulby Road | 25/01548 /OUT ** | 2028/29: 20; 2029/30: 20; 2030/31: 8 | 48
|  |  | 48 homes | 62 homes
|  | Billesdon | B2: Billesdon Depot south of Gaulby Road |  | 2028/29: 5; 2029/30: 5 | 10
10 Homes
|  | Billesdon | B3: Former Lorry Park Gaulby Road |  | 2029/30: 5 | 5
5 homes
|  | Great Bowden | GB1: Land north of Dingley Road | 25/00608 /FUL * | 2028/29: 5; 2029/30: 10 | 15
|  |  | 15 Homes | 11 Homes
|  | Great Bowden | GB2: Land off Dingley Road and Nether Green (GREAT BOWDEN) |  | 2028/29: 25; 2029/30: 25; 2030/31: 25; 2031/32: 10 | 85
85 Homes
|  | Houghton on the Hill | HH1: Land north of Uppingham Road | 25/00599 /OUT* | 2028/29: 25; 2029/30: 25; 2030/31: 25; 2031/32: 5 | 80
|  |  | 80 homes | 90 homes
|  | Houghton on the Hill | HH2: Land north of Stretton Lane | 24/00359 /FUL *** | 2028/29: 12; 2029/30: 12 | 24
|  |  | 24 Homes | 24 homes
|  | Husband Bosworth | HB1: Land east of Welford Road | 26/00470 /OUT ** | 2029/30: 50; 2030/31: 50; 2031/32: 5 | 105
|  |  | 105 Homes | 150 Homes
|  | Ullesthorpe | U1: Land south of Ashby Road | 25/01537 /OUT * | 2028/29: 15; 2029/30: 15 | 30
|  |  | 30 Homes | 46 Homes
|  | Ullesthorpe | U2: Land north of Ashby Road |  | 2028/29: 25; 2029/30: 25 | 50
50 Homes
| Small Villages | see list below | Small Villages (see table below) |  |  | 23.3333 | 23.3333 | 23.3333 | 23.3333 | 23.3333 | 23.3333 | 23.3333 | 23.3333 | 23.3333 | 23.3333 | 23.3333 | 23.3333 | 23.3333 | 23.3333 | 23.3333 |  |  |  |  | 349.9995
|  |  |  | Total | 0 | 63.3333 | 73.3333 | 405.3333 | 465.3333 | 526.3333 | 538.3333 | 493.3333 | 633.3333 | 633.3333 | 603.3333 | 473.3333 | 433.3333 | 433.3333 | 393.3333 | 263.3333 | 575 | 575 | 575 | 565 | 8721.9995
|  |  | * Approved Subject to S106 |  | 2025/26: ** Planning Application Submitted; 2028/29: *** Planning Application Refused; 2031/32: **** This site (LSGR) is a cross-boudary site with AP4 (Land South of Gartree Road). The Harborough part of the site can accommodate 3,150 homes. 850 homes will be delivered in OWBC under the AP4 allocation. The site can therefore accommodate 4,000 homes intotal across both authority areas.
6431.9995
HDC Small Village Housing Requirement by Settlement
| HDC Small Village Requirement |  | Number of Homes delivered by 2041
|  | Arnesby | 11
|  | Bitteswell | 29
|  | Church Langton | 2
|  | Claybrooke Magna | 31
|  | Dunton Bassett | 49
|  | Foxton | 22
|  | Gilmorton | 7
|  | Great Easton | 31
|  | Hallaton | 15
|  | Leire | 23
|  | Lubenham | 28
|  | Medbourne | 7
|  | North Kilworth | 8
|  | South Kilworth | 14
|  | Swinford | 8
|  | Tilton | 27
|  | Tugby | 14
|  | Walcote | 24
|  | Total | 350